## Slide 1: IDP/BUDGET & PMS REP FORUM PRESENTATION ON 2023/2024 IDP/BUDGET & PMS PROCESS PLAN AUGUST 2022
“Sikhula Simanyene”
Presented by: Cllr.S.S.Maneli
Mayor

## Slide 2
PRESENTATION OUTLINE
INTRODUCTION
PURPOSE OF THE PROCESS PLAN
2023/2024 IDP/BUDGET & PMS PROCESS PLAN PHASES
INSTITUTIONAL ARRANGEMENTS
ROLES AND RESPONSIBILITIES
CONCLUSION

## Slide 3
INTRODUCTION
As required by the Municipal Systems Act (Act 32 of 2000), Municipal Council, within a prescribed period , must adopt a process plan set out in writing to guide the planning, drafting, adoption and review of its Integrated Development Plan (IDP).
The municipality must through appropriate mechanisms, processes and procedures established, consult the local community before adopting the process plan.

## Slide 4
PURPOSE OF THE PROCESS PLAN
To allow the community to participate in the setting of appropriate key performance indicators and performance targets for the Municipality
To depict and commit on time frames for smooth running and sequence of activities
Cost estimates with dedicated involvement from specific role players in the Municipality.

## Slide 5
PHASES OF THE PROCESS PLAN.
Planning Phase
July - August
Develop process plan indicating activities, time frames and assigned responsibilities .
Situational Analysis Phase
October - December
What is happening and ensure that the decision will base on the situation/Community priority need
Strategies, Project and Programs Phase
January - March
Integration and Approval Phase
Strategic Planning session – Programs ,Projects identification for implementation. Table draft IDP and Budget to Council for adoption.

## Slide 6
PHASE 1: PLANNING PHASE
.
PHASE 1: DEVELOPMENT OF 2023/2024 IDP/PMS & BUDGET PROCESS PLAN FROM JULY – SEPTEMBER 2022 Tabling and Approval of 2023/2024 IDP/PMS & Budget Process Plan. |  |  |  | 
NO | DATE | ACTIVITY | MODE OF COMMUNICATION | RESPONSIBLE PERSON’S
1. | 25 August 2022 | IDP/PMS& Budget Steering Committee (2023/2024 Process plan) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
2. | 29 August 2022 | IDP/PMS& Budget Rep Forum Meeting (2023/2024 Process plan) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
3. | 30 August 2022 | Council Meeting (Approval 2023/2024 Process plan | Contact Session | Mayor/Speaker/Councillors/Municipal Manager and HOD’s
4. | 5 September 2022 | Budget Circular providing guidance on compilation of staff budgets (initiate the budget process) | Contact Session, Audio, Print and Electronic media | CFO
5. | 15 September 2022 | Inter-Governmental Relations Forum (IGR) | Contact Session | Mayor/Municipal Manager/HOD’s

## Slide 7
PHASE 2: SITUATIONAL ANALYSIS
 | PHASE 2: SITUATIONAL ANALYSIS FROM OCTOBER –DECEMBER 2021 Conduct Situational Analysis for 2022/2023) |  |  | 
NO | DATE | ACTIVITY | MODE OF COMMUNICATION | RESPONSIBLE PERSON’S
6. | 5-7 October 2022 | MPAC Roadshow on Annual Report | Contact Session, Audio, Print and Electronic Media | Mayor/Municipal Manager/HOD’s
7. | 10 November 2022 | IDP/PMS& Budget Steering Committee (Situational analysis) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
8. | 17 November 2022 | Inter-Governmental Relations Forum (IGR) | Contact Session | Mayor/Municipal Manager/HOD’s
9. | 23 November 2022 | IDP/PMS& Budget Rep Forum ((Situational analysis) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
10. | 30 November 2022 | Submission of Operating Budget and Capital Estimates to the Finance and Budget Office | Contact Session, Audio, Print and Electronic media | HOD’s
 |  | Draft or review budget related policies such credit control and indigent policy, tariff policy, budget policy etc. | Contact Session, Audio, Print and Electronic media | CFO

## Slide 8: PHASE 3: DEVELOPING STRATEGIES
 | PHASE 3: STRATEGIES FROM JANUARY -MARCH 2023 (Conduct Strategic Planning Session, 2021/22 Annual Report Roadshows, Tabling and Adopting Draft 2023/2024 IDP/Budget) |  |  | 
NO | DATE | ACTIVITY | MODE OF COMMUNICATION | RESPONSIBLE PERSON’S
11. | 2nd February 2023 – 3rd February 2023 | Technical Strategic Planning | Contact Session, Audio, Print and Electronic media | Municipal Manager/HOD’s/IDP & PMS Manager
12. | 14 -17 February 2023 | Institutional Strategic Planning | Contact Session, Audio, Print and Electronic media | Mayor/Speaker/Council/Municipal Manager and HOD’s
13. | 21 February 2023 | 2023 Mid-Year Engagement with Provincial Treasury | Contact Session, Audio, Print and Electronic media | Municipal Manager/HOD’s
14. | 27 February 2023 | Tabling of a revised budget through adjustment budget | Contact Session, Audio, Print and Electronic media | Mayor/Speaker/Council/Municipal Manager and HOD’s
15. | 1st March 2023 | Consolidate and prepare proposed budget and plans for next financial years considering previous year performance as per audited financial statements | Contact Session, Audio, Print and Electronic media | Municipal Manager/HOD’s
16. | 3rd March 2023 | Tabling of 2021/22 Annual Report (MPAC Annual Report Roadshows) | Contact Session, Audio, Print and Electronic media | Mayor/Speaker/MPAC Chairperson/Municipal Manager and HOD’s
17. | 14 March 2023 | IDP/PMS& Budget Steering Committee (Draft 2023/2024 IDP) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
18. | 24 March 2023 | IDP/PMS& Budget Rep Forum (Draft 2023/2024 IDP) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
19. | 30 March 2023 | Special NLM Council (2023/24 Draft IDP/Budget/SDBIP) | Contact Session | Mayor/Speaker/Councillors/Municipal Manager and HOD’s

## Slide 9: PHASE 4: INTEGRATION OF SECTOR PLAN AND APPROVAL OF IDP
PHASE 4: INTERGRATION OF SECTOR PLANS AND APPROVAL OF IDP& BUDGET FROM APRIL – JUNE 2023 (Align Sector Plans and Final Approval of 2023/2024 IDP and Budget) |  |  |  | 
NO | DATE | ACTIVITY | MODE OF COMMUNICATION | RESPONSIBLE PERSON’S
20. | 5th April 2023 | Drafts IDP/ Budget publicized for public comments | Contact Session, Audio, Print and Electronic media | Municipal Manager/ CFO
21. | 19 & 21 April 2023 | IDP/Budget Roadshows (Final 2023/2024 IDP/Budget) | Contact Session, Audio, Print and Electronic media | Mayor/Councillors/Municipal Manager/HOD’s
22. | 28 April 2023 | Draft Budget Benchmark and Engagement Date 2023 | Contact Session, Audio, Print and Electronic media | Mayor/Councillors/Municipal Manager/HOD’s
23. | 4 May 2023 | Prepare the final budget documentation for approval considering any other new information of a material nature | Contact Session, Audio, Print and Electronic media | Municipal Manager /CFO
24. | 12 May 2023 | IDP/PMS& Budget Steering Committee (2022/2023 IDP/Budget/SDBIP) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s

## Slide 10: PHASE 4: INTEGRATION OF SECTOR PLAN AND APPROVAL OF IDP
PHASE 4: INTERGRATION OF SECTOR PLANS AND APPROVAL OF IDP& BUDGET FROM APRIL – JUNE 2023 (Align Sector Plans and Final Approval of 2023/2024 IDP and Budget) |  |  |  | 
NO | DATE | ACTIVITY | MODE OF COMMUNICATION | RESPONSIBLE PERSON’S
25. | 23 May 2023 | Inter-Governmental Relations Forum (IGR) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
26. | 25 May 2023 | IDP/PMS& Budget Rep Forum (2022/2023 IDP/Budget/SDBIP) | Contact Session, Audio, Print and Electronic media | Mayor/Municipal Manager/HOD’s
27. | 30 May 2023 | Council Meeting (Final 2022/2023 IDP and Budget) | Contact Session, Audio, Print and Electronic media | Mayor/Speaker/Councillors/Municipal Manager and HOD’s
28. | 6 June 2023 | Approved IDP Review and Budget published/advertised | Contact Session, Audio, Print and Electronic media | Mayor/Councillors/Municipal Manager/HOD’s
29. | 28 June 2023 | Approval of Final 2023/2024 SDBIP | Contact Session, Audio, Print and Electronic media | Mayor/Councillors/Municipal Manager/HOD’s
30. | 30 June 2023 | Submit annual budget reports to National & Provincial Treasuries and District Municipality. Notify department of Local Government in the province about the budget approval. | Contact Session, Audio, Print and Electronic media | Municipal Manager

## Slide 11: INSTITUTIONAL ARRANGEMENTS
The IDP preparation process requires an extensive consultation and participation of communities, all role players and key stakeholders in order to achieve shared understanding of the municipal development trajectory and alignment.
The Municipality is utilizing the follow institutional arrangements.

## Slide 12: INSTITUTIONAL ARRANGEMENT
STRUCTURE | COMPOSITION | TERMS OF REFERENCE
IDP and Budget Steering Committee | Chairperson: Mayor. Executive Committee, Council, Traditional Leaders, Senior Management, Representative from District Municipality and COGTA. | Considers the Budget and IDP Process Plan for the municipality Agrees on budget principles to be adopted Monitors adherence to the Budget Process Plan Makes content recommendations
IDP and Budget Representative Forum | Chairperson: Mayor. Executive Committee, Council, Traditional Leaders, Administration and all stakeholders | Represent the interests of constituents in the IDP and budget processes Ensure communication between all stakeholder representatives including the municipal government. Monitor the performance of the planning and implementation processes.

## Slide 13: INSTITUTIONAL ARRANGEMENT
STRUCTURE | COMPOSITION | TERMS OF REFERENCE
District IDP And PMS Forum | Chairperson: Executive Mayor. All Mayors from LM’s, ADM Council & Traditional Leaders, ADM Senior Management, Rep from LM’s and Sector Departments. | To ensure coordination of the implementation of the planning, budget, reporting and review process to promote and improve the performance of the municipalities. Facilitate review of the District and local municipalities’ IDP and PMS policies and frameworks to ensure compliance. Responsible for forward planning and performance planningmatters.

## Slide 14: ROLES AND RESPONSIBILITIES
MAYOR
The Mayor of Ngqushwa Local Municipality has the ultimate responsibility for the preparation and implementation of the IDP, Budget & Performance Management. In his capacity the Mayor has to:
Be responsible for the overall oversight, development and monitoring of the process or delegate IDP & PMS responsibilities to the Municipal Manager;
Ensure that the budget, IDP & budget related policies are mutually consistent & credible;
Submit the revised IDP & the Annual Budget to the municipal Council for adoption;
Submit the proposed Performance Management System to the municipal Council for adoption.
Responsible for the overall co-ordination and initiation of the review process
COUNCIL’S EXECUTIVE COMMITTEE:
Monitor the Implementation of the IDP, involved in decision making process and provide recommendation to Council.
COUNCILLORS ,TRADITIONAL LEADERS & WARD COMMITTEES
Assist and facilitate in public consultation and participation
Provide comment on the IDP
Consider and adopt the process plan and reviewed IDP
Ensure integration of IDP, Budget and the Performance Management System(

## Slide 15: ROLES AND RESPONSIBILITIES
MUNICIPAL MANAGER
Prepare the Framework and Process Plan;
Undertake the overall management and co-ordination of the planning process;
Ensure that all relevant actors are appropriately involved;
Nominate persons in charge of different roles;
Be responsible for the day- to-day management of the drafting process;
Ensure that the planning process is participatory, strategic and implementation orientated and is aligned with and satisfies sector planning requirements;
Respond to comments on the draft IDP from the public, horizontal alignment and other spheres of government to the satisfaction of the municipal council;
Ensure proper documentation of the results of the planning of the IDP document;
Adjust the IDP in accordance with the MEC for Local Government’s proposals; and
The Municipal Manager may delegate these functions to an IDP Manager

## Slide 16: ROLES AND RESPONSIBILITIES
HEAD OF DEPARTMENTS
Must provide relevant technical, sector and financial information for analysis for
determining priority issues;
Must contribute technical expertise in the consideration and finalization of strategies and identification of projects;
Must provide departmental operational and capital budgetary information;
Must be responsible for the preparation of project proposals, the integration of projects and sector programmes; and
Must be responsible for preparing amendments to the draft Integrated Development Plan for submission to municipal Council for approval.
National and Provincial Sector Departments and Social Partners
Align planning, budgeting, implementation process with the District Framework Plan

## Slide 17: ROLES AND RESPONSIBILITIES
EXTERNAL STAKEHOLDER
External stakeholders play an important part in the review of the IDP :
Represents the interests of their constituents in the IDP process;
Inform the Council what their development needs are, and to participate actively in determining the municipality’s development direction;
Analyze issues, contribute in setting of priorities, negotiate and reach consensus;
Discuss and comment on the draft IDP-, budget, policies and by-laws; and
Monitor IDP-budget performance and implementation

## Slide 18: CONCLUSION
After consultation with all stakeholders, 2023/24 IDP/Budget & PMS process plan must be submitted to Council meeting for approval by the end of August 2022.
Hard copies of the process plan can be accessed from the office of the Municipal Manager / Ngqushwa website.